## Project Plan
Project Plan
WEEK #1 (22/01/20 - 28/01/20)
Member Name | Task Name | Task Type | Start Date | Deadline | Actual Start Date | Actual End Date | Description & Comments
Caroline Youssef | Prepare "HSI" | Non - Technical | 2020-01-22 | 2020-01-28 | 2020-01-22 | 2020-01-24 | Review Points were opened by Eng. Mohamed Ali
Mahmoud Gamal | Prepare "HSI" | Non - Technical | 2020-01-22 | 2020-01-28 | 2020-01-22 | 2020-01-24 | Review Points were opened by Eng. Mohamed Ali
Hesham El Sherbini | Prepare CYRS | Non - Technical | 2020-01-22 | 2020-01-28 | 2020-01-22 | 2020-01-24 | Review Points were opened by Eng. Mohamed Ali
Mirna Anis | Prepare CYRS | Non - Technical | 2020-01-22 | 2020-01-28 | 2020-01-22 | 2020-01-24 | Review Points were opened by Eng. Mohamed Ali
Mark Joseph | Prepare CYRS | Non - Technical | 2020-01-22 | 2020-01-28 | 2020-01-22 | 2020-01-24 | Review Points were opened by Eng. Mohamed Ali
Mahmoud Hamdy | Send SIQ | Non - Technical | 2020-01-23 | 2020-01-30 | 2020-01-23 | 2020-01-24 | SIQ was sent to Eng. Mohamed Ali and questions were answered
WEEK #2 (29/01/20 - 04/02/20)
Member Name | Task Name | Task Type | Start Date | Deadline | Actual Start Date | Actual End Date | Description & Comments
Caroline Youssef | Address review points on "HSI" | Non - Technical | 2020-01-25 | 2020-01-31 | 2020-01-27 | 2020-01-30 | Review Points were resolved and new points opened by Eng. Mohamed Ali
Mahmoud Gamal | Address review points on "HSI" | Non - Technical | 2020-01-25 | 2020-01-31 | 2020-01-27 | 2020-01-30 | Review Points were resolved and new points opened by Eng. Mohamed Ali
Hesham El Sherbini | Address review points on "CYRS" | Non - Technical | 2020-01-22 | 2020-01-28 | 2020-01-28 | 2020-01-29 | Review Points were resolved and new points opened by Eng. Mohamed Ali
Mirna Anis | Address review points on "CYRS" | Non - Technical | 2020-01-22 | 2020-01-28 | 2020-01-28 | 2020-01-29 | Review Points were resolved and new points opened by Eng. Mohamed Ali
Mark Joseph | Address review points on "CYRS" | Non - Technical | 2020-01-22 | 2020-01-28 | 2020-01-28 | 2020-01-29 | Review Points were resolved and new points opened by Eng. Mohamed Ali
Mahmoud Hamdy | Make Modifications to SIQ format as excel sheet | Non - Technical | 2020-01-25 | 2020-01-27 | 2020-01-30 | 2020-01-30 | Task was delayed due to illness
WEEK #3 (05/02/20 - 11/02/20)
Member Name | Task Name | Task Type | Start Date | Deadline | Actual Start Date | Actual End Date | Description & Comments
Caroline Youssef | Address review points on "HSI" | Non - Technical | 2020-02-05 | 2020-02-12 | 2020-02-05 | 2020-02-10 | Review Points were resolved and new points opened by Eng. Mohamed Ali
Mahmoud Gamal | Update project Plan & Help in "HSI" | Non - Technical | 2020-02-05 | 2020-02-06 | 2020-02-05 | 2020-02-10 | Review Points were resolved and new points opened by Eng. Mohamed Ali
Hesham El Sherbini | Address review points on "CYRS" | Non - Technical | 2020-02-05 | 2020-02-12 | 2020-02-05 | 2020-02-10 | All review points were resolved and document was released
Mirna Anis | Address review points on "CYRS" | Non - Technical | 2020-02-05 | 2020-02-12 | 2020-02-05 | 2020-02-10 | All review points were resolved and document was released
Mark Joseph | Address review points on "HSI" | Non - Technical | 2020-02-05 | 2020-02-12 | 2020-02-05 | 2020-02-10 | Review Points were resolved and new points opened by Eng. Mohamed Ali
Mark Joseph | Prepare "SRS" | Non - Technical | 2020-02-05 | 2020-02-12 | 2020-02-05 | 2020-02-06 | Review points were opened
Mahmoud Gamal | Prepare "SRS" | Non - Technical | 2020-02-05 | 2020-02-12 | 2020-02-05 | 2020-02-06 | Review points were opened
Hesham El Sherbini | Prepare "SRS" | Non - Technical | 2020-02-05 | 2020-02-12 | 2020-02-05 | 2020-02-06 | Review points were opened
Mahmoud Hamdy | [6 empty] | No Task Was Assigned due to illness
WEEK #4 (12/02/20 - 18/02/20)
Member Name | Task Name | Task Type | Start Date | Deadline | Actual Start Date | Actual End Date | Description & Comments
Caroline Youssef | Address review points on "HSI" | Non - Technical | 2020-02-12 | 2020-02-17 | 2020-02-12 | 2020-02-15 | All Review points were resolved
Mahmoud Gamal | Address review points on "HSI" | Non - Technical | 2020-02-12 | 2020-02-17 | 2020-02-12 | 2020-02-15 | All Review points were resolved
Mark Joseph | Address review points on "HSI" | Non - Technical | 2020-02-12 | 2020-02-17 | 2020-02-12 | 2020-02-15 | All Review points were resolved
Mahmoud Hamdy | [6 empty] | No Task Was Assigned due to illness
WEEK #5 (19/02/20 - 27/02/20)
Member Name | Task Name | Task Type | Start Date | Deadline | Actual Start Date | Actual End Date | Description & Comments
Mahmoud Hamdy | Reform Project Plan according to history | Non - Technical | 2020-02-21 | 2020-02-22 | 2020-02-21 | 2020-02-22 | Uploaded Project Plan and waiting for Eng. Mohamed Ali's feedback
Caroline Youssef | Internal Audit on changes made to documents | Non - Technical | 2020-02-21 | 2020-02-27
Mahmoud Gamal | Resolve points in "SRS" | Non - Technical | 2020-02-22 | 2020-02-23
Hesham El Sherbini | Resolve points in "SRS" | Non - Technical | 2020-02-22 | 2020-02-23
Mirna Anis | Internal Audit on changes made to documents | Non - Technical | 2020-02-21 | 2020-02-27
Mark Joseph | Prepare GDD | Non - Technical | 2020-02-25 | 2020-02-27
Mahmoud Hamdy | Prepare GDD | Non - Technical | 2020-02-25 | 2020-02-27