## HSI
Date | Reviewer | Review point | Acceptance | Point status | Comment
24/1/2020 | Ali | Good job for the SIQ online form, but please provide a sheet for SIQ with my answers and commit it in the input documets directoy | Accepted | Closed | Mali 30/1/2020: Point is closed
24/1/2019 | Ali | Document status section shall be a table with the following coloms --> "Version, Date , Auther,Status " |  | Open | Mali 30/1/2020: Still open
24/1/2020 | Ali | As mentioned in SIQ online form, startup animation modes are according to input signal called "Mode" provided by input switch "Mode switch" so fig.1 shall be updated to indicate that you have an input switch. | Accepted | Closed | Mali 30/1/2020: Point is closed
24/1/2020 | Ali | Output LEDs shall be more declared in the block diagram: --> Right TI --> Left TI --> Tail |  | Open | Mali 30/1/2020: Still open
24/1/2020 | Ali | Merge the 2 figures in one figure as they are in the same system no need to split | Accepted | Closed | Mali 30/1/2020: Point is closed
24/1/2020 | Ali | In figure 3: right and left LEDs are connected with the same output signal. For example R1 and L1 will be activated at the same time if Pin30 is HIGH while every single LED in TI function shall have its own output. Why ? Because TI function is the "Turn Indicator" function so if you are driving and turning right, the right TI LED branch shall be activated (not the right and left together) also if you are turning left, the left TI LED branch shall be activated (not the right and left together). NOTE: TI function LEDs shall be activated with the declared animation style mentioned in CRS | Accepted | Closed | Mali 30/1/2020: Point is closed
24/1/2020 | Ali | In Features section: 3rd feature is called "TI" --> Turn indicator not "T1" | Accepted | Closed | Mali 30/1/2020: Point is closed
30/1/2020 | Ali | Version 1.0.1 shall be 1.1 |  | Open
30/1/2020 | Ali | Inblock diagram please add 2 switches for TI function (Right TI and Let TI) |  | Open
30/1/2020 | Ali | TI output LEDs name is wrong it's written "T1 LEDs" |  | Open

## CYRS
Date | Reviewer | Review point | Acceptance | Point status | Comment
24/1/2021 | Ali | Document status section shall be a table with the following coloms --> "Version, Date , Auther,Status " |  | Open | Mali 30/1/2020: Still open
24/1/2022 | Ali | Block diagram isn't correct, it shall be a block has input signals(Tail signal - right TI signal - left TI signal - Mode signal) and has outputs (LEDs) |  | Open | Mali 30/1/2020: Still open
30/1/2020 | Ali | There are no requirements in CYRS |  | Open