## Project Plan
Project Plan
Member Name | Task Name | Task Type | Start Date | Deadline | Estimated Duration (Days) | Description & Comments
Mahmoud Hamdy Mohamed Hassan | Send SIQ an | Non - Technical | 2020-01-23 | 2020-01-30 | 7
Caroline | Prepare HIS | Non - Technical | 2020-01-22 | 2020-01-28 | 6
Mahmoud Gamal | Prepare HIS | Non - Technical | 2020-01-22 | 2020-01-28 | 6
Hesham El Sherbini | Prepare CYRS | Non - Technical | 2020-01-22 | 2020-01-28 | 6
Mirna Anis | Prepare CYRS | Non - Technical | 2020-01-22 | 2020-01-28 | 6
Mark Joseph | Prepare SRS | Non - Technical | 2020-01-22 | 2020-01-28 | 6

## Schedule
Schedule
Milestone | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date | Description & Comments
Complete CYRS | 2020-01-22 | 2020-01-22 | 2020-01-23 |  | Currently working on modifications asked by Eng. Mohamed Ali
Complete HIS | 2020-01-22 | 2020-01-22 | 2020-01-23 |  | Currently working on modifications asked by Eng. Mohamed Ali
Complete SRS | 2020-01-22 | 2020-01-22 | 2020-01-23 |  | Currently working on modifications asked by Eng. Mohamed Ali
Complete project plan and SIQ based on data from CYRS | 2020-01-23 | 2020-01-22 | 2020-01-24 |  | Currently working on modifications asked by Eng. Mohamed Ali