## CYRS
Date | Reviewer | Review point | Acceptance | Point status | Comment
2020-06-02 | Ali | Current Document State section is empty please move the status table to this section |  | Open
2020-06-02 | Ali | Please provide every SRS requirement in a table like the one In the presentation |  | Open
2020-06-02 | Ali | Requirements IDs shall be like the following format : Req_PO5_LSAN_ SRS_01-V01 |  | Open
2020-06-02 | Ali | Req_ PO5_LSAN_ SRS_Start animation mode 1_01: it shall be "Mode switch" not "pin switch" |  | Open
2020-06-02 | Ali | Req_ PO5_LSAN_ SRS_Start animation mode 1_02-V01: "set flag to TRUE" not "set flag so as" |  | Open
2020-06-02 | Ali | Req_ PO5_LSAN_ SRS_Start animation mode 1_02-V01: splite this requirement to 2 requirements one to set a flag to TRUE when the switch is pressed and another to enter mode one when the flag is TRUE |  | Open
2020-06-02 | Ali | Req_ PO5_LSAN_ SRS_Start animation mode 1_03-V01: Please provide a determined delay not "e.g: 1000" |  | Open
2020-06-02 | Ali | Req_ PO5_LSAN_ SRS_Start animation mode 2_01-V01: Duplicated with requirement "o Req_ PO5_LSAN_ SRS_Start animation mode 1_01-V01" |  | Open
2020-06-02 | Ali | Req_ PO5_LSAN_ SRS_Start animation mode 2_02-V01: Same point as raw 7 |  | Open
2020-06-02 | Ali | Req_ PO5_LSAN_ SRS_Start animation mode 2_03-V01: - Mode 2 not 1 -Please provide a determined delay not "e.g: 1000" |  | Open
2020-06-02 | Ali | Remove these requirements: -Req_ PO5_LSAN_ SRS_Tail Function High_03-V01 -Req_ PO5_LSAN_ SRS_Tail Function Low_01-V01 -Req_ PO5_LSAN_ SRS_Tail Function Low_03-V01 -Req_ PO5_LSAN_ SRS_Right Turn Indicator On_03-V01 -Req_ PO5_LSAN_ SRS_Right Turn Indicator Off_01-V01 -Req_ PO5_LSAN_ SRS_Right Turn Indicator Off_03-V01 -Req_ PO5_LSAN_ SRS_Left Turn Indicator On_03-V01 - Req_ PO5_LSAN_ SRS_Left Turn Indicator Off_01-V01 - Req_ PO5_LSAN_ SRS_Left Turn Indicator Off_03-V01 |  | Open
2020-06-02 | Ali | Add also HIS in the reference table |  | Open